RIDE-HAILING BACKEND

Project Sprint Plan

2 Developers  •  2–3 hrs/day  •  12 Weeks  •  6 Sprints

| TOTAL SPRINTS 6 | DURATION 12 Weeks | DAILY HOURS 2–3 hrs | TEAM SIZE 2 Devs |
| --- | --- | --- | --- |

# What You Will Build

A production-grade backend for a ride-hailing platform (like Uber/Ola) with 4 microservices, each tackling a distinct hard problem in Java backend engineering.

| 📍 LocationService Real-time driver tracking via Redis geospatial. Handles 5000+ location events/sec reactively. | 🎯 MatchingService Race-condition-free driver assignment. Lock-free concurrency with Java 21 Virtual Threads. | 🚗 TripService Complete trip lifecycle via Kafka event pipeline. Saga pattern for distributed transactions. | 🔔 NotificationSvc Async event-driven notifications. Circuit breaker + retry patterns via Resilience4j. |
| --- | --- | --- | --- |

# Tech Stack

| Layer | Technology | What You Learn |
| --- | --- | --- |
| Language | Java 21 (Virtual Threads, Records, Sealed Classes) | Modern Java features in production context |
| Framework | Spring Boot 3 + WebFlux | Reactive non-blocking programming |
| Async / Events | Apache Kafka + Project Reactor | Event-driven architecture, backpressure |
| Cache / Geo | Redis + Redisson client | Geospatial queries, TTL, distributed cache |
| Primary DB | PostgreSQL + HikariCP + Flyway | Connection pooling, migrations, read replicas |
| History DB | Apache Cassandra | Wide-column store, partition key design |
| Resilience | Resilience4j | Circuit breaker, rate limiter, retry |
| Observability | OpenTelemetry + Jaeger + Grafana | Distributed tracing, metrics dashboards |
| Testing / Load | JUnit 5 + TestContainers + Gatling | Integration tests, load testing |
| Infra | Docker + Docker Compose | Local multi-service environment |

# Sprint Timeline at a Glance

| Sprint | Theme | Primary Focus | Deliverable |
| --- | --- | --- | --- |
| S1 · Wk 1–2 | Foundation | Project setup, domain modeling, REST APIs | 4 services running, full CRUD, Swagger docs |
| S2 · Wk 3–4 | Location | Redis geo, reactive WebFlux, backpressure | Live driver tracking at 5000 events/sec |
| S3 · Wk 5–6 | Concurrency | Locks, Virtual Threads, optimistic locking | Zero duplicate matches under 1000 concurrent req |
| S4 · Wk 7–8 | Events | Kafka pipeline, Saga, idempotency, DLQ | Full trip lifecycle event-driven |
| S5 · Wk 9–10 | Persistence | CQRS, Cassandra, read replicas, HikariCP | Polyglot DB, CQRS working, query optimized |
| S6 · Wk 11–12 | Production | Tracing, circuit breakers, load test, demo | Grafana dashboard, Jaeger traces, load test report |

# Detailed Sprint Plans

Each sprint runs for 2 weeks (10 working days). Daily bandwidth: 2–3 hours per developer. Day numbers below represent working days within each sprint.

## Sprint 1 (Week 1–2): Project Setup & Core Domain Modeling

🎯 Sprint Goal: Monorepo scaffolded, all services skeletons running, core entities defined, Docker environment working

🛠 Tech Focus: Spring Boot 3, Java 21, Docker Compose, PostgreSQL, MapStruct, Lombok

| 📅 Sprint 1 (Week 1–2): Project Setup & Core Domain Modeling |  |  |  |  |
| --- | --- | --- | --- | --- |
| Day | Dev 1 Tasks | Dev 2 Tasks | End-of-Day Goal |
| 1 | Init monorepo, multi-module Maven/Gradle setup | Setup Docker Compose (Postgres, Redis, Kafka, Zookeeper) | docker-compose up runs all infra locally |
| 2 | Scaffold 4 service modules: matching, location, trip, notification | Setup shared-lib module (common DTOs, exceptions, constants) | All 4 services start with /health endpoint |
| 3 | Design core entities: Driver, Rider, Trip (JPA + Flyway migrations) | Design DriverLocation, MatchRequest, TripEvent entities | ERD finalized, tables created via Flyway |
| 4 | Implement Repository layer + basic CRUD for Driver & Rider | Implement Repository layer for Trip & MatchRequest | CRUD APIs working for all entities |
| 5 | Driver & Rider REST APIs with validation (Jakarta Bean Validation) | Trip REST APIs + global exception handler + error DTOs | Postman collection ready, all APIs tested |
| 6 | Add Spring Security skeleton (JWT structure, no auth logic yet) | Add Swagger/OpenAPI docs to all 4 services | API docs accessible at /swagger-ui |
| 7 | Sprint review, integration smoke test, fix issues, push to Git | Write README per service, document setup steps | Code merged to main, demo-ready |

## Sprint 2 (Week 3–4): Location Service & Redis Geospatial

🎯 Sprint Goal: Real-time driver location tracking working end-to-end with Redis geospatial queries

🛠 Tech Focus: Redis GEOADD/GEORADIUS, Redisson, WebFlux, Spring Data Redis

| 📅 Sprint 2 (Week 3–4): Location Service & Redis Geospatial |  |  |  |  |
| --- | --- | --- | --- | --- |
| Day | Dev 1 Tasks | Dev 2 Tasks | End-of-Day Goal |
| 1 | Integrate Redisson client in LocationService, configure Redis connection pool | Design DriverLocationDTO, write Redis key schema (driver:location:{id}) | Redis connectivity confirmed, key design documented |
| 2 | Implement GEOADD: driver location update endpoint (POST /location) | Implement GEORADIUS query: findNearbyDrivers(lat, lng, radiusKm) | Location stored and queried from Redis |
| 3 | Add location expiry (TTL): driver removed if no ping in 30s | Add driver status filter in geo query (only AVAILABLE drivers) | Stale drivers auto-expire from geo index |
| 4 | WebFlux: convert LocationService to reactive (Mono/Flux) | Add backpressure handling on location update stream | Non-blocking endpoints, reactive pipeline |
| 5 | Load test: simulate 500 drivers pinging location every 2s (Gatling) | Observe Redis memory under load, tune connection pool settings | Benchmark report: ops/sec, latency p99 |
| 6 | Implement location history (last 10 positions) stored in Postgres async | Write scheduled cleanup job for stale location data | Location history persisted without blocking main flow |
| 7 | Sprint review, refactor hot paths from profiling, document Redis schema | Write integration tests for geo queries with TestContainers | All location tests green, TestContainers running |

## Sprint 3 (Week 5–6): Matching Service & Concurrency Deep Dive

🎯 Sprint Goal: Race-condition-free driver matching under high concurrency — the hardest sprint

🛠 Tech Focus: ReentrantLock, ConcurrentHashMap, Optimistic Locking, Java 21 Virtual Threads, JFR

| 📅 Sprint 3 (Week 5–6): Matching Service & Concurrency Deep Dive |  |  |  |  |
| --- | --- | --- | --- | --- |
| Day | Dev 1 Tasks | Dev 2 Tasks | End-of-Day Goal |
| 1 | Implement naive matching (no locking) — intentionally broken baseline | Write concurrent test: 100 threads, same driver, first-come-first-served | Reproduce the race condition, document it |
| 2 | Fix with pessimistic locking (synchronized) — measure throughput hit | Fix with ReentrantLock — compare throughput vs synchronized | Benchmark: synchronized vs ReentrantLock |
| 3 | Implement optimistic locking with @Version in JPA on Driver entity | Handle OptimisticLockException: retry logic with exponential backoff | Optimistic locking working, retries handled |
| 4 | Implement lock-free matching using ConcurrentHashMap + compareAndSet | Profile all 4 approaches with JFR (Java Flight Recorder) | Performance comparison report across 4 strategies |
| 5 | Switch matching service thread pool to Java 21 Virtual Threads | Benchmark Virtual Threads vs platform threads under 1000 concurrent matches | Virtual thread benchmark complete |
| 6 | Implement match timeout: if driver doesn't accept in 30s, re-match | Add match scoring algorithm (distance + driver rating weight) | Smart matching with timeout and scoring |
| 7 | Sprint review, write detailed concurrency doc explaining all approaches | Stress test final implementation: 1000 concurrent match requests | Zero duplicate matches under max load |

## Sprint 4 (Week 7–8): Kafka Event Pipeline & Trip Lifecycle

🎯 Sprint Goal: Complete trip lifecycle (request → match → start → complete → pay) fully event-driven via Kafka

🛠 Tech Focus: Apache Kafka, Consumer Groups, Saga Pattern, Idempotency Keys, Dead Letter Queue

| 📅 Sprint 4 (Week 7–8): Kafka Event Pipeline & Trip Lifecycle |  |  |  |  |
| --- | --- | --- | --- | --- |
| Day | Dev 1 Tasks | Dev 2 Tasks | End-of-Day Goal |
| 1 | Setup Kafka topics: ride.requested, driver.matched, trip.started, trip.completed | Configure consumer groups per service, set partition count = 3 | Topics created, consumers connected |
| 2 | TripService: produce ride.requested event when rider books | MatchingService: consume ride.requested, produce driver.matched | Event flows: booking triggers matching |
| 3 | TripService: consume driver.matched, update trip state, produce trip.started | NotificationService: consume all events, send push notification stubs | Full event chain: request → match → start |
| 4 | Implement idempotency keys on all Kafka consumers (dedup on event ID) | Implement Dead Letter Queue (DLQ) for failed message processing | Exactly-once processing, failed msgs in DLQ |
| 5 | Implement Saga: trip cancellation flow (compensating transactions) | Implement Saga: payment failure rollback (refund ride, re-queue driver) | Saga compensation working for 2 failure scenarios |
| 6 | Add Kafka consumer lag monitoring with Micrometer metrics | Simulate consumer crash mid-trip — verify recovery and state consistency | Crash recovery test passing, metrics visible |
| 7 | Sprint review, draw complete event flow diagram, update docs | End-to-end integration test: full trip lifecycle via events | Full trip e2e test passing |

## Sprint 5 (Week 9–10): DB Scaling, CQRS & Distributed Transactions

🎯 Sprint Goal: Polyglot persistence working — right DB for each access pattern, CQRS implemented

🛠 Tech Focus: CQRS, PostgreSQL Read Replicas, Cassandra, HikariCP tuning, 2PC vs Saga

| 📅 Sprint 5 (Week 9–10): DB Scaling, CQRS & Distributed Transactions |  |  |  |  |
| --- | --- | --- | --- | --- |
| Day | Dev 1 Tasks | Dev 2 Tasks | End-of-Day Goal |
| 1 | Setup Cassandra for ride history, design partition key (rider_id + month) | Implement TripHistoryRepository (write to Cassandra post-trip-complete) | Ride history writes to Cassandra |
| 2 | Implement CQRS in TripService: separate Command (write) and Query (read) models | Build TripQueryService: reads from denormalized read model in Postgres | CQRS working — commands and queries separated |
| 3 | Configure Postgres read replica in Docker, route read queries to replica | Implement HikariCP separate pools: write pool → primary, read pool → replica | Read/write split with separate connection pools |
| 4 | Implement distributed transaction problem: atomically update Redis + Postgres on trip start | Compare approaches: 2PC (why it fails) vs Saga (why it works here) | Document tradeoffs, implement Saga solution |
| 5 | Add database-level indexes for hot query paths (driver lookup, trip history) | Run EXPLAIN ANALYZE on top 5 queries, fix N+1 issues with JOIN FETCH | Query performance report, slow queries fixed |
| 6 | Implement database connection pool stress test (exhaust pool, observe behavior) | Add HikariCP metrics to Micrometer + Grafana dashboard | DB metrics visible in Grafana |
| 7 | Sprint review, finalize data access layer, document DB choices rationale | Integration tests for CQRS, Cassandra writes, read replica routing | All DB tests green |

## Sprint 6 (Week 11–12): Observability, Resilience & Polish

🎯 Sprint Goal: Production-grade observability, circuit breakers, distributed tracing, resume-worthy demo

🛠 Tech Focus: OpenTelemetry, Jaeger, Resilience4j, Micrometer, Grafana, Gatling final load test

| 📅 Sprint 6 (Week 11–12): Observability, Resilience & Polish |  |  |  |  |
| --- | --- | --- | --- | --- |
| Day | Dev 1 Tasks | Dev 2 Tasks | End-of-Day Goal |
| 1 | Add OpenTelemetry Java agent to all 4 services, export traces to Jaeger | Instrument Kafka producer/consumer with trace context propagation | One trace spans all 4 services in Jaeger UI |
| 2 | Add Resilience4j Circuit Breaker on MatchingService → LocationService calls | Configure fallback: if LocationService is down, use last known location | Circuit opens on failure, fallback activates |
| 3 | Add Resilience4j Rate Limiter on ride booking endpoint (50 req/s per user) | Add Retry with exponential backoff on Kafka publish failures | Rate limiting and retry working |
| 4 | Add Micrometer custom metrics: match_latency_ms, concurrent_trips, queue_depth | Build Grafana dashboard: 4 golden signals (latency, traffic, errors, saturation) | Live Grafana dashboard showing all metrics |
| 5 | Final Gatling load test: 10,000 concurrent virtual users, 30 min sustained | Monitor system under load: find and fix bottlenecks | Load test report: p50/p95/p99 latencies |
| 6 | Write architecture decision records (ADRs) for top 5 design decisions | Record a 5-min demo video: full trip flow + Jaeger trace + Grafana | Demo video + ADRs complete |
| 7 | Final review: clean up code, update README with architecture diagram | Update GitHub README with tech stack badge, system diagram, how to run | GitHub repo interview-ready |

# Recommended Daily Routine (2–3 hrs)

| Time Block | Duration | Activity |
| --- | --- | --- |
| Start | 15 min | Sync: brief standup — what did I do yesterday, what am I doing today, any blockers? |
| Core Work | 90–120 min | Deep focus coding — no interruptions. Each dev works on their assigned tasks. |
| Review | 20 min | Code review each other's work, pair on any blockers, update task status. |
| Wrap-up | 10 min | Push code to Git, update notes, jot down questions for next session. |

# Dev Split Strategy

The two developers are split by service ownership — not by frontend/backend. This ensures both devs deeply learn all 4 hard areas.

| Dev 1 — Core Systems Owner - Primary: MatchingService (concurrency focus) - Secondary: LocationService (reactive/Redis) - Cross-cutting: Docker infra, CI setup - Load testing with Gatling - Architecture decision records (ADRs) | Dev 2 — Data & Events Owner - Primary: TripService (Kafka + Saga) - Secondary: NotificationService (resilience) - Cross-cutting: Kafka setup, schema registry - Observability: Grafana + Jaeger dashboards - Integration tests with TestContainers |
| --- | --- |

# Definition of Done — Per Sprint

- All assigned tasks committed to Git with meaningful commit messages

- At least one integration test per new feature using TestContainers

- No broken builds — CI passes on the main branch

- README updated with any new setup instructions

- Both devs have reviewed and understood each other's code

- Performance benchmark captured (latency, throughput) where relevant

- Any architecture decisions documented in an ADR file

# What You Can Say in Interviews After This Project

| Topic | What You Can Confidently Discuss |
| --- | --- |
| Concurrency | Compared 4 locking strategies under load with JFR profiling — chose lock-free CAS for hot path |
| Virtual Threads | Benchmarked Java 21 Virtual Threads vs platform threads at 1000 concurrent requests |
| Reactive | Built non-blocking pipeline handling 5000 events/sec with Project Reactor backpressure |
| Kafka / Saga | Implemented Saga pattern for distributed transactions with DLQ and idempotency keys |
| DB Scaling | Designed CQRS with separate read replicas and polyglot persistence (Postgres + Cassandra + Redis) |
| Resilience | Configured circuit breakers, rate limiters, and retries with Resilience4j in production-like setup |
| Observability | Built end-to-end distributed traces across 4 services with OpenTelemetry and Grafana dashboards |

Good luck — build something interview-worthy. 🚀